## Dashboard
NomadVPN Pro - Marketing Launch Tracker
Last Updated: December 23, 2025
KEY METRICS - MONTH 1 TARGETS
Metric | Target | Actual | % Complete
Website Visitors | 500 | 0 | 0
Email Subscribers | 50 | 0 | 0
Reddit Upvotes | 100 | 0 | 0
YouTube Views | 500 | 0 | 0
Consultations Booked | 5 | 0 | 0
Customers | 3 | 0 | 0
Revenue ($) | 2100 | 0 | 0
REVENUE TRACKER
Service Tier | Price | Qty Sold | Revenue
Essential Setup | 699 | 0 | 0
Premium + Support | 1299 | 0 | 0
Remote VPN Access (monthly) | 50 | 0 | 0
TOTAL REVENUE |  |  | 0

## Market Research
MARKET RESEARCH - DEMAND VALIDATION
Validation Score: 9.0/10 - Massive Validated Demand
VALIDATION FACTORS
Factor | Score | Evidence
Question Volume | 10/10 | Questions posted DAILY across 5+ platforms
Recent Growth | 10/10 | Accelerating 2024-2025 (matured from 'is this possible' to 'what's best way')
User Frustration | 9/10 | Repeated 'how do I' despite free DIY guides existing
Willingness to Pay | 8/10 | KeepYourHomeIP has paying customers at premium prices
Technical Barrier | 9/10 | 15-20 hours DIY, networking knowledge required
Market Size | 9/10 | 18.1M US digital nomads, 22M remote workers
Competition | 3/10 | Very few turnkey commercial services exist
COMPETITOR ANALYSIS
Competitor | Offering | Pricing | Key Quote/Evidence | Your Advantage
KeepYourHomeIP | Preconfigured routers + VPN server setup | $200-500+ (business) | "Routers arrived preconfigured...worked from Spain" | Same service, competitive pricing, Fortune 500 tested
Rocky in Reel Time | YouTube content + consulting | Unknown consulting | Uses identical Flint 2 + Beryl AX stack | Turnkey product vs hourly consulting
Commercial VPNs | Data center VPN service | $3-15/month | Users complain: "gets detected and blocked" | Residential IP unblockable
DIY Raspberry Pi | Self-configured VPN server | $50-100 hardware | Requires 15-20 hours + Linux expertise | Zero technical knowledge needed
TOP QUESTIONS FROM FORUMS (Exact Quotes)
Question | Platform | Date | Relevance | Opportunity
How can I work remotely from another country when my company does not allow? | r/VPN | Dec 2023 | GATEWAY | $699 Essential Setup
What's a foolproof way to hide my location from my employer? | r/VPN | Feb 2023 | HIGH INTENT | Turnkey solution
Living outside USA with remote job. Is a VPN really necessary? | r/remotework | Feb 2025 | EDUCATION | Content marketing
Traveling while working. Need to hide location. Is this VPN method legit? | r/digitalnomad | Sep 2021 | VALIDATION | Your exact hardware
How to work remotely with VPN - no software needed | r/digitalnomad | Jul 2022 | DIY FATIGUE | Done-for-you service
Working from overseas - how to avoid VPN detection by employer? | r/remotework | Apr 2025 | CURRENT | GL.iNet named specifically
VPN'ing into work from another country | r/VPN | Apr 2022 | NEED HELP | No friend/family needed
How many of you are hiding your location from your employer? | r/digitalnomad | Feb 2025 | MAINSTREAM | Pre-trip testing add-on
Is it possible to hide location from company VPN? | r/digitalnomad | Apr 2022 | TECHNICAL | Your Flint2+Beryl model
Working remotely abroad with VPN? | r/VMwareHorizon | Jun 2023 | SHORT TERM | Rental packages opportunity
TARGET CUSTOMER PROFILE
Attribute | Details
Age Range | 25-45
Income | $60K-150K+ (white collar remote)
Industries | Tech, marketing, creative, consulting
Tech Level | Tech-savvy but NOT network engineers
Use Case 1 | Extended Travel: 2-6 months abroad (largest segment)
Use Case 2 | Family Obligations: 2-8 weeks caring for relatives
Use Case 3 | Digital Nomad Testing: 2-4 weeks trial
Use Case 4 | Short Business Travel: 2-3 days (rental opportunity)
Pain: Technical | "I'm not technical at all" - recurring theme
Pain: Time | Spending 15-20 hours researching/configuring
Pain: Fear | Detection anxiety - job loss risk
Pain: Reliability | Commercial VPNs too slow or blocked
CONTENT OPPORTUNITIES
Type | Title/Keyword | Intent Level | Priority
YouTube | How I've Worked from 15 Countries Without My Employer Knowing | HIGH | Week 3
YouTube | GL.iNet Flint 2 Complete Setup Guide for Remote Workers | HIGH | Week 2
YouTube | Why Commercial VPNs Fail for Remote Work | MEDIUM | Week 4
Blog/SEO | work remotely from another country (keyword) | HIGH VOLUME | Week 2
Blog/SEO | hide location from employer VPN (keyword) | HIGH CONVERSION | Week 3
Blog/SEO | GL.iNet Flint 2 setup guide (keyword) | VERY HIGH CONV | Week 2
Reddit Post | I've been working remotely from abroad using GL.iNet for 2+ years... | AUTHORITY | Week 2
Reddit AMA | Fortune 500 VPN expert - AMA about working abroad securely | LEADS | Week 5
MESSAGING VALIDATION
Type | Message | User Response
❌ AVOID | Hide from your employer | Users reject deceptive framing
❌ AVOID | Deceive your company | Negative association
❌ AVOID | Break the rules | Too risky sounding
✅ USE | Privacy protection for remote work | Positive framing
✅ USE | Secure international connectivity | Professional tone
✅ USE | Work from anywhere while maintaining security | Value-focused
✅ USE | Enterprise-tested VPN setup | Credibility builder
✅ USE | Zero detection track record | Results-focused

## 90-Day Timeline
90-DAY LAUNCH TIMELINE
Week | Phase | Task | Due Date | Status | Notes
Week 1 | Foundation | Apply GL.iNet Affiliate Program | 2025-12-24 01:57 | Not Started | https://www.gl-inet.com/affiliate-program/
Week 1 | Foundation | Apply GL.iNet Reseller Program | 2025-12-24 01:57 | Not Started | https://www.gl-inet.com/form/become-a-reseller/
Week 1 | Foundation | Create Reddit Account | 2025-12-24 01:57 | Not Started | u/NomadVPNPro or similar
Week 1 | Foundation | Start Reddit Commenting (build karma) | 2025-12-30 01:57 | Not Started | 10+ helpful comments on r/digitalnomad, r/GlInet
Week 1 | Foundation | Set up Email Capture | 2025-12-28 01:57 | Not Started | ConvertKit or Mailchimp free tier
Week 2 | Foundation | Create Lead Magnet PDF | 2026-01-02 01:57 | Not Started | Travel Router Comparison Guide 2025
Week 2 | Foundation | Join GL.iNet Forum | 2025-12-31 01:57 | Not Started | Introduce yourself, be helpful
Week 2 | Foundation | Script First YouTube Video | 2026-01-06 01:57 | Not Started | GL.iNet Flint 2 Complete Setup Guide
Week 3 | Content Launch | First Reddit Educational Post | 2026-01-07 01:57 | Not Started | Use template from MARKETING_PLAYBOOK.md
Week 3 | Content Launch | Publish First YouTube Video | 2026-01-13 01:57 | Not Started | GL.iNet Flint 2 Setup Guide
Week 3 | Content Launch | First Blog Post Live | 2026-01-13 01:57 | Not Started | SEO-optimized for 'gl inet flint 2 vpn setup'
Week 4 | Content Launch | GL.iNet Affiliate Approved | 2026-01-20 01:57 | Not Started | Add links to all content
Week 4 | Content Launch | Collect Beta Testimonials | 2026-01-20 01:57 | Not Started | From any early conversations
Week 5 | Amplification | Reddit AMA Post | 2026-01-27 01:57 | Not Started | Fortune 500 VPN expert AMA
Week 6 | Amplification | Second YouTube Video | 2026-02-03 01:57 | Not Started | Best Travel Router 2025
Week 6 | Amplification | Email Sequence Automated | 2026-02-03 01:57 | Not Started | 5-email welcome sequence
Week 7 | Amplification | Third YouTube Video | 2026-02-10 01:57 | Not Started | Commercial vs Home VPN
Week 8 | Amplification | GL.iNet Reseller Approved | 2026-02-17 01:57 | Not Started | Wholesale pricing active
Week 8 | Amplification | Consider Reddit Ad Test | 2026-02-17 01:57 | Not Started | $100-200 test budget
Week 9 | Optimization | Analyze Traffic Sources | 2026-02-24 01:57 | Not Started | Google Analytics review
Week 10 | Optimization | Double Down on Winners | 2026-03-03 01:57 | Not Started | Scale what's working
Week 11 | Optimization | Launch Referral Program | 2026-03-10 01:57 | Not Started | $100-200 per referral
Week 12 | Optimization | Collect Video Testimonials | 2026-03-17 01:57 | Not Started | From first customers
Week 12 | Optimization | Plan Q2 Strategy | 2026-03-23 01:57 | Not Started | Review and adjust

## Reddit Tracker
REDDIT MARKETING TRACKER
Subreddit Targets
Subreddit | Members | Priority | Posts Made | Comments Made | Upvotes Earned | Leads Generated | Notes
r/digitalnomad | 2M+ | High | 0 | 0 | 0 | 0 | Primary target - educational posts
r/GlInet | 15K | Very High | 0 | 0 | 0 | 0 | Technical audience, receptive
r/VPN | 500K | High | 0 | 0 | 0 | 0 | Commercial vs residential content
r/remotework | 400K | High | 0 | 0 | 0 | 0 | Work-from-anywhere focus
r/homelab | 2M | Medium | 0 | 0 | 0 | 0 | Technical setup guides
r/overemployed | 200K | Medium | 0 | 0 | 0 | 0 | Stealth work solutions
TOTALS |  |  | 0 | 0 | 0 | 0
Post History
Date | Subreddit | Post Title | Type | Upvotes | Comments | Leads | Link

## YouTube Tracker
YOUTUBE CONTENT TRACKER
Video Content Plan
Video Title | Target Keywords | Status | Publish Date | Views | Likes | Comments | Subscribers Gained | Leads
GL.iNet Flint 2 Complete Setup Guide | gl inet flint 2 setup, wireguard home server | Not Started |  | 0 | 0 | 0 | 0 | 0
Best Travel Router 2025 - Beryl AX Review | best travel router, beryl ax review | Not Started |  | 0 | 0 | 0 | 0 | 0
Why Commercial VPNs Fail for Remote Work | vpn for remote work, nordvpn blocked | Not Started |  | 0 | 0 | 0 | 0 | 0
Work From Anywhere Setup Guide | digital nomad vpn, work remotely abroad | Not Started |  | 0 | 0 | 0 | 0 | 0
Home VPN vs NordVPN Comparison | home vpn vs nordvpn, residential vpn | Not Started |  | 0 | 0 | 0 | 0 | 0
TOTALS |  |  |  | 0 | 0 | 0 | 0 | 0
Channel Metrics
Total Subscribers | 0
Total Views | 0
Watch Time (hours) | 0
Click-through Rate (%) | 0

## Customers
CUSTOMER & LEAD TRACKER
Date | Name | Email | Phone | Source | Service Tier | Status | Revenue | Notes | Testimonial? | Referral Source
SUMMARY
Total Leads | 0
Consultations | 0
Converted | 0
Total Revenue | 0

## Expenses
EXPENSE TRACKER
Date | Category | Description | Amount | Notes
| Hardware Inventory | 2x Flint 2 + 3x Beryl AX | 800 | Initial fulfillment stock
| Email Marketing | ConvertKit/Mailchimp | 0 | Free tier initially
| Video Equipment | Phone + free editing | 0 | Use existing equipment
| Reddit Ads | Test budget (optional) | 0 | After organic traction
| Domain/Hosting | Already deployed | 0 | Railway + Cloudflare
TOTAL EXPENSES |  |  | 800
BUDGET SUMMARY
Planned Budget | 1200
Actual Spent | 800
Remaining | 400

## Reddit Templates
REDDIT POST TEMPLATES
TEMPLATE 1: Educational Story Post (r/digitalnomad)
Title: How I've Been Working Remotely From Abroad for 2+ Years (My Setup) Hey everyone, I've seen a lot of questions lately about VPNs and working abroad, so I wanted to share what's actually worked for me. **The Problem**: Commercial VPNs (NordVPN, ExpressVPN) use data center IPs that get detected and blocked. I learned this the hard way when [Slack/Zoom/company VPN] flagged my connection from Portugal. **The Solution**: I set up my own WireGuard VPN server at home using a GL.iNet Flint 2 router. When I travel, I bring a Beryl AX travel router that connects to my home server. My traffic exits through my actual residential IP - identical to working from my living room. **Results**: - Tested across [Nike/AT&T/government networks] - zero detection - 50+ countries over 3 years - Speed: ~80% of my home connection (depends on local internet) **Hardware**: - Home: GL.iNet Flint 2 ($130) - Travel: GL.iNet Beryl AX ($110) - Kill switch enabled (drops connection if VPN fails) Happy to answer questions about the setup. I also offer [free guides / setup services if you want it done for you]. --- [Include disclaimer: This is for legitimate privacy/security purposes. Always check your employment contract.]
TEMPLATE 2: Technical Problem-Solution (r/VPN)
Title: Why Commercial VPNs Fail for Remote Work (And What Actually Works) If you're trying to work abroad while connected to your employer's VPN, commercial VPN services usually won't cut it. Here's why: **The Detection Problem**: Your company's IT can see the IP address you're connecting from. Commercial VPNs use data center IPs that are: 1. In public databases as "VPN/proxy" 2. Shared by thousands of users 3. Flagged by security tools like Cisco Umbrella, Zscaler, etc. **The Solution**: Residential IP via home VPN server Instead of routing through NordVPN's data center, route through your actual home connection: Home Setup: - GL.iNet Flint 2 router running WireGuard server - Connects to your home ISP (residential IP) - Port forwarding through your modem Travel Setup: - GL.iNet Beryl AX (fits in your bag) - Pre-configured to connect to your home server - All devices connect to this router via WiFi/Ethernet - Kill switch drops connection if tunnel fails **Why This Works**: Your employer sees the same IP they'd see if you were at home. Because you ARE connecting through your home. I've tested this with Fortune 500 companies including [telecom, retail, government] networks. Zero detection incidents. Questions welcome. I also help people set this up if the technical side is overwhelming.
TEMPLATE 3: AMA Format (r/digitalnomad)
Title: I've helped 50+ remote workers set up home VPNs for international travel. AMA about staying connected abroad. Background: - 3+ years building VPN setups for digital nomads - Tested across 50+ countries - Clients include people working for Fortune 500 telecom, retail, and government agencies - Zero detection incidents across all clients What I can answer: - Technical setup questions (GL.iNet routers, WireGuard, kill switches) - What DOESN'T work (commercial VPNs, most "solutions" on YouTube) - Speed expectations (realistic benchmarks) - Risk assessment (what can actually be detected and how) - Hardware recommendations for different budgets What I won't help with: - Anything illegal in your jurisdiction - Bypassing actual security controls for malicious purposes I'm not here to sell anything - just want to share what I've learned. Fire away! [If someone asks about professional setup, mention you offer services but keep focus on free help]
COMMENTING GUIDELINES (Build Karma First)
RULE: 10 helpful comments for every 1 promotional post Sample Helpful Comments: 1. When someone asks "How do I hide my location?": "The key is using a residential IP, not a data center IP. Set up a WireGuard server at home (I use GL.iNet Flint 2) and connect to it via travel router. Your traffic exits through your home IP - identical to working from your couch." 2. When someone recommends NordVPN/ExpressVPN: "Commercial VPNs use data center IPs that are in public databases. Most enterprise security tools (Cisco Umbrella, Zscaler) flag these automatically. Home VPN server with residential IP is the way to go." 3. When someone asks about hardware: "GL.iNet Flint 2 for home ($130) + Beryl AX for travel ($110) is the sweet spot. Both support WireGuard natively. Just remember to enable kill switch on the travel router." 4. When someone shares their setup: "Nice setup! One thing I'd add - make sure you're using WireGuard not OpenVPN. Much faster and harder to detect. Also enable the kill switch in case your tunnel drops." NEVER: - Post links to your service unprompted - Be pushy or salesy - Argue with people who disagree - Spam the same comment in multiple threads